## Sheet1
Task/Phase | Oct 10 - 24 | Oct 25 - Nov 7 | Nov 8 - 21 | Nov 22 - Dec 5 | Dec 6 - 19 | Dec 20 - Jan 7
Data Collection & Cleaning
Data Pre-processing
Database & Architecture Setup
LLM Selection
RAG Testing & Model Evaluation
Final Testing & Refinement
Research Report